## Task
Task | Owner | Notes | Milestones Due Dates | Status
Cleaning up existing model | Katarina | Upload to Git when complete. Ask Randy about index weirdness. | 2013-11-17 | Complete
Create git repository and add users | Xuefeng |  | 2013-11-17 | Complete
Develop check constraints | Ben |  | 2013-11-20 | Complete
Surrogate keys (make sequences for each table) | Xuefeng |  | 2013-11-20 | Complete
MEETING |  |  | 2013-11-20 | Complete
Business Rule Triggers | Ben | 1. Stage Option Limit 2. Stage option markup 3. House style within subdivision options. | 2013-11-26 | Complete | Didn't make house style trigger. New field needs to be added to the selected options table: price
Denormalized Table | Katarina | Just find it | 2013-11-26
Populate database with dummy data | Katarina, Sonal |  | 2013-11-26
Views | Xeufeng | 1. Status of all unfinishing homes 2. All empty lots | 2013-11-26 | Complete | Need to double check if end_date is initilized as Null and house_id in lot is Null
Create 2 roles w/ different priveleges | Ben | Construction Manager, Sales Agent | 2013-11-26 | Complete
Create at least 1 DB job | Xuefeng | ???? | 2013-11-26
Data Warehousing Plan | Ben |  | 2013-11-26 | Complete
Create a few alternate indexes | Sonal | ???? | 2013-11-26
Reports/Procedures | Xuefeng | 1. Status of a given customer's home 2. Status of a employees (like where construction worker is assigned) 3. For a given house, the status of tasks | 2013-11-26 | 3 is not completed | 1.Need more exceptions! 2.Not sure how to do the third report. How to get to the right table?? 3. All emplyees have construction_project _id?
MEETING |  |  | 2013-11-26
Presentation |  |  | 2013-12-09
SUBMIT PROJECT |  |  | 2013-12-09
Tasks:
Database level authentication
Object Description Document
Entity Description Document
Requirements Document
Data Dictionary
List all transaction requirements that are associated with the case study
assumptions
Database User Guide
The folowing are finished???
check constraints
table constraints
mandatory columns enforced where required participation enforced for foreign keys default values enforced where appropriate look-up tables
database triggers

## Trigger
controlling the price markup for an option item that is after the last stage
disallows a selection of a stage above